## Gantt Chart
BrightTV Case Study — Project Gantt Chart
20-minute presentation for CVM team · 10-day sprint
| Task | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | Timing
| Phase 1 · Data preparation & environment setup | [10 empty] | Day 1
Convert UTC → SAST (UTC+2)
Data profiling & quality checks
Session-level data model
| Phase 2 · Exploratory analysis & insight generation | [10 empty] | Days 2–5
User & usage trends
Consumption drivers
Low-consumption day analysis
Supplementary data sourcing
| Phase 3 · Strategy & recommendations | [10 empty] | Days 6–8
Content recommendations
User-base growth initiatives
KPI framework & success metrics
| Phase 4 · Presentation build & delivery | [10 empty] | Days 9–10
Slide deck build
Rehearsal & polish
| Presentation delivery | [9 empty] | ◆
Legend
Phase 1 · Data prep
Phase 2 · Analysis
Phase 3 · Strategy
Phase 4 · Delivery
|  | ◆ | Milestone (presentation delivery)